Ghana Country Water Partnership

GHANA COUNTRY WATER PARTNERSHIP

WATER, CLIMATE AND DEVELOPMENT

PROGRAMME (WACDEP)

REVISED WORK PLAN 2013 - 2015

JUNE 2013

EXECUTIVE SUMMARY

This project document has been prepared to implement in Ghana the assistance the  Global Water Partnership is giving African Governments to support integration of water security and climate resilience in their transboundary and national development planning and decision- making processes. The project responds to the declaration of the African Heads of State at Sharm el Sheikh in 2008 on Water and Sanitation in Africa. It also responds to AMCOW’s request to GWP in 2009 and its own work programme over 2010-2013.

The project in Ghana will be implemented over a 3-year period at a cost of 600,000. It will be financed by the Austrian Development Agency (ADA), the Department for International Development (DFID), The Danish International Development Agency (DANIDA) and other donors.

The beneficiaries will include the planning units and their staff in the sector ministries including NDPC, MOFEP, MWRWH, MOFA, MOE, MLNR, EPA, Metropolitan, Municipal and District Assemblies. The ultimate beneficiaries will be the farmers/fishermen/herdsmen on the farms.

Implementation will be by Ghana Country Water Partnership with the assistance of the Global and the West African Regional Partnerships. The project will be managed by national Project Steering Committee comprising representatives of the MOFEP, NDPC, WRC, MOFA, EPA, FC and MLGRD.  The secretariat for the Steering Committee will be provided by that of the CWP-Ghana.

The overall objective is to assist to enhance technical and institutional capacity and predictable financing and investments in water security and climate change adaptation for economic growth and human security.

The assistance will be in i) Identification of  water and related sector projects in the National Development Plan ii) The selection and implementation of projects which are water secure and climate resistant iii) Assistance with knowledge and capacity building iv) Assistance with partnership and project management

The document is based on general Terms of Reference prepared by GWP Africa and AMCOW and was adapted to suit the situation in Ghana.

The project will be reported annually in accordance to a reporting format developed by GWP.

A log-frame has been provided which will be used for Monitoring and Evaluation.

Finally, the project will be used to strengthen the CWP-Ghana in the areas of engaging stakeholders, strengthening the network, fund raising and monitoring and evaluation.

|  | IMPLEMENTATION PLAN: WATER CLIMATE AND DEVELOPMENT PROJECT |
| --- | --- |
|  | WEST AFRICA/GHANA |
|  | Impact: A higher level of water security and climate resilience achieved in developing countries, trans-boundary basins and economic regions |
|  | Outcome: Increased availability of acceptable quantity and quality of water for all beneficial uses, and increased capacity and ability of regions, countries and communities to adapt to climatic variability |
| Work Package | Activity | Task | Output | RESPONSIBLE /PARTNERS | BUDGET (‘ 000) |
|  |  |  |  |  | Q3 ‘12 | Q4 ‘12 | Q1 ‘13 | Q2 ‘13 | Q3 ‘13 | Q4 ‘13 | 2014 | 2015 | Total |
| OUTPUT 1: Countries and regions supported to develop and integrate 'no regrets' water security and climate resilience investments into their development plans, budgets and programmes | Output indicator 1: Number of countries with approved 'no regrets' investment and financing strategy documents on water security and climate resilient development Output indicator 2: Number of countries supported in the development of projects to access climate and climate-related funds Output indicator 3: Number of river basin organisations (including trans-boundary) applying tools for improved water security and climate resilience |
| Work Package 1: Regional and Trasboundary Cooperation | Support AMCOW, African Union and Regional Economic Communities such as SADC, ECOWAS, ECCAS, EAC/IGAD to advance regional cooperation in climate change adaptation in Transboundary waters and shared aquifers for regional and economic development |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.1.1 | Not applicable |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.1.2 | Not applicable |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.1.3 | Not applicable |  |  |  |  |  |  |  |  |  |  |  |  |
| Work Package 2: National development planning processes | Support to integration of water security and climate resilience into national development planning, decision-making processes | Indicator: Number of legal frameworks / policies / strategies, sectoral and development plans- integrating water security and climate resilience |  |  | 0 | 15 | 15 | 10 | 0 | 0 | 40 |
|  |  | Key output: National development plans and/or sectoral plans that include Water Security and Climate Resilience |  |  |  |  |  |  |  |  |  |
| Activity 1.2.1 | Undertake a national assessment by reviewing Policies, Strategies and programmes of the NDPC and SSDP…………… | Identify the Sector Policies, and the Sector Strategic Development Programmes (long and medium term) and the water and water related projects in water and sanitation, food, energy, environment, etc. submitted to the NDPC | Report containing the SSDPs of the agencies, the water projects submitted to NDPC under GSGDA, the ones screened for WS & CR and the method and processes used. | National Consultant, WRC, NDPC |  |  | 0 | 15 | 10 | 0 | 0 | 0 | 25 |
|  |  | Identify which projects have been screened for a) water security b) for climate resilience by the WRC and c) the processes and methods used to get them admitted into the national development plan. |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.2.2 | Carry out a Stakeholder engagement and Institutional analysis etc | Convene workshop of stakeholders NDPC, MOFEP, MWRWH, MOFA, MOE, MOTC, MEST, MLNR, MLGRD, WRC, CWSA, GWCL, FC, EPA, MMDAs etc. to discuss and comment on findings particularly with regard to screening methods and the procedures for submission to NDPC taking into account those to be made available through the Capacity Building of WP 7. | Workshop report containing comments and suggestions on report | G-CWP, WRC NDPC, etc. |  |  | 0 | 0 | 5 | 0 | 0 | 0 | 5 |
| Activity 1.2.3 | Review National adaptation responses to ensure that sectors invest in water security and climate resilience…….. | Identify water related development in sectors like highways, forestry, mining housing, environment etc | Report containing projects in water related sectors, methods used for adaptation to climate change and use of the methods to propose guidelines where they do not exist | MOFEP, MWRWH, MOFA, MOE, MOTC, MEST, MLNR, MLGRD, WRC, CWSA, GWCL, VRA, FC, EPA, MMDAs, etc. |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 10 |
|  |  | Identify water components in their development assess how they can be adapted to withstand the disasters due to water security and climate change |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Prepare guidelines for screening such projects for investment analysis using outputs of WP 7. |  |  |  |  |  |  |  |  |  |  |  |
| Work Package 3: Investments | Support the development of approved gender sensitive ‘No/low Regrets’ investment and financing strategy document | Indicator: No. of investment strategies supporting policies and plans which integrate water security for climate resilience |  |  | 0 | 0 | 0 | 0 | 17 | 10 | 27 |
|  |  | Key output: ‘No/low regrets' investment and financing strategy document on water security and climate resilient development |  |  |  |  |  |  |  |  |  |
| Activity 1.3.1 | Prioritise selected projects for Investment analysis | Classify the projects passing the screening test into sectors (water and sanitation, food, energy and environment.) | Report containing the list of projects in each of water and sanitation, food, energy and environment sectors prioritised | Consultant, NDPC CWSA, GWCL MOFA, VRA, EPA WRC, and MMDAs |  |  | 0 | 0 | 0 | 0 | 6 | 0 | 6 |
|  |  | Prioritise projects in each sector taking into account the social economic and ecological impacts, the need for balanced development across the regions and districts, mainstream gender, the poor, and marginalized. |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.3.2 | Appraise and analyse Investment options | Select those that fall within a predetermined range | Report containing findings on the investment analysis and financing options | NDPC CWSA, GWCL MOFA, VRA, EPA WRC, and MMDAs |  |  | 0 | 0 | 0 | 0 | 6 | 10 | 16 |
|  |  | Carry out an investment analysis on them. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Carry out financial analysis to assess financing options |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.3.3 | Assess investment analysis capacity and organise a forum on investment planning | Use WP 6 to assess the capacity of the institutions and staff to carry out the functions above | Staff in planning units of agencies identified for training. | National Training Coordinator, Consultant |  |  | 0 | 0 | 0 | 0 | 2 | 0 | 2 |
| Activity 1.3.4 | Prepare Investment Plan and integrate into national development plans and mainstreaming into planning systems | Select projects that meet criteria set | National investment Plan with projects which are water secure, climate resilient and are bankable (no/low regret) integrated. This will enable decisions to be made to look for funding from various sources (national treasury, agencies recovering full or partial costs like projects of GWCL or VRA, development partners, special funding sources etc.) | Consultant, NDPC, CWSA, GWCL MOFA, VRA, EPA WRC, and MMDAs |  |  | 0 | 0 | 0 | 0 | 3 | 0 | 3 |
|  |  | Organise an investment forum involving the stakeholder institutions to agree on the findings of the investment analysis and the financing options |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Submit the agreed list to the NDPC as the investment plan of the water and sanitation, food, energy and environment sectors |  |  |  |  |  |  |  |  |  |  |  |
|  |  | NDPC integrates the water sector investment plan into the overall national investment plan and submits it to the MOFEP for the appropriate funding options to be sources to be determined |  |  |  |  |  |  |  |  |  |  |  |
| Work Package 4: Project Preparation and Financing | Support governments to enhance efficiency in Project preparation and leverage funding from traditional sources of water financing and adaptation funds | Indicator: Number of countries supported by GWP in the development of projects to access climate and climate-related funds |  |  | 0 | 0 | 0 | 10 | 8 | 25 | 43 |
|  |  | Key output: Projects prepared by governments and prioritised for funding |  |  |  |  |  |  |  |  |  |
| Activity 1.4.1 | Enabling Project Preparation | Compile information on various funding facilities. Assess the awareness and capacity of the planning units of MOFEP, MWRWH, MOFA, MOE, MOTC, MEST, MLNR, MLGRD, WRC, CWSA, GWCL, VRA, FC, EPA, MMDAs etc. to use them. | Report Containing on various funding facilities | Consultant, MOFEP and the planning units of the MMDAs |  |  | 0 | 0 | 0 | 0 | 3 | 5 | 8 |
| Activity 1.4.2 | Appraise and classify existing investment projects | Appraise and classify the water and water –related investment projects integrated into the national investment plan into those that relate to the different funding facilities | Report with a list of projects in investment plan assigned to different funding facilities. | Consultant, MOFEP and the planning units of the MMDAs |  |  | 0 | 0 | 0 | 0 | 0 | 15 | 15 |
| Activity 1.4.3 | To Broker and Bridge Gap in Knowledge | Prepare a report on Project Preparation Facilities for Water Security and Climate Resilience in Ghana highlighting the areas of innovative and new financing mechanisms and sources. | Workshop report on project preparation using the methods of different funding sources. | Consultant, MOFEP and the planning units of the MMDAs |  |  | 0 | 0 | 0 | 10 | 5 | 0 | 15 |
|  |  | Share and disseminate the report with the funding agencies. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Organise Project Preparation workshop |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.4.4 | Mobilize Resources | Carry out consultations with the relevant funding agencies to reach agreement on the no/low regret investment projects in the national investment plan the funding agencies wish to support and thereafter use their specific guidelines to prepare projects for funding. | Report on experience in using different Project Preparation methods | Consultant, MOFEP and the planning units of the MMDAs |  |  | 0 | 0 | 0 | 0 | 0 | 5 | 5 |
| OUTPUT 2 : Solutions in place for addressing critical water security challenges to enhance climate resilience of countries and communities | Output indicator 2.1: Number of GWP supported demonstration projects on water security and climate resilience undertaken Output indicator 2.2: Number of documented cases of replication of solutions developed through GWP network Output indicator 2.3: Number of agreements and high level national and global policy and technical documents providing global and regional leadership on cutting edge issues for water security and climate resilience Output indicator 2.4: Recognition of GWP contribution to the global debate measured by number of acknowledgments in official documents |
| Work Package 5: Demonstration Projects | Implement innovative sub national pro-poor and gender sensitive solutions to generate lessons | Indicator: -Number of beneficiaries supported in demonstration projects on water security and climate resilience undertaken -Number of documents produced outlining the lessons from GWP demonstration projects and a plan for replicating solutions -Number of demonstration projects undertaken for which innovation has been demonstrated |  |  | 0 | 5 | 15 | 13 | 125 | 65 | 223 |
|  |  | Key output: Innovative green (i.e. sustainable) solutions in place that address critical water security challenges that enhance climate resilience of countries and communities |  |  |  |  |  |  |  |  |  |
| Activity 2.1.1 | Consultations with stakeholders | Carry out consultations and sensitise stakeholders (WRC, MOFA, Forestry Commission, Fisheries Commission, GIDA, CWSA, Traditional Authorities, MLNR , MOWAC, SADA, etc.) in the Bawku Municipality and the Bawku West and Bongo districts of the Upper East Region | Consulted and sensitised stakeholders | GWP/CWP |  |  | 0 | 5 | 15 | 0 | 25 | 10 | 55 |
| Activity 2.1.2 | Baseline survey | Carry out a baseline survey and situation analysis in the area with regard to the flooding and its impacts and the adaptation and coping mechanisms that have been developed. | A report outlining the current situation as to the on socio economic and environmental impact of flooding the area. | Consultant, GWP/CWP |  |  | 0 | 0 | 0 | 13 | 10 | 0 | 23 |
| Activity 2.1.3 | Intervention project and investment analysis | Identify intervention options to mitigate adverse impacts | Report outlining No regret intervention options | Consultant, GWP/CWP |  |  | 0 | 0 | 0 | 0 | 25 | 25 | 50 |
|  |  | Screen options to ensure their water security and climate resilience and |  |  |  |  |  |  |  |  |  |  |  |
|  |  | carry out investment analysis to ensure intervention is no/low regret project |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.1.4 | Submission to NDPC and MOFEP | Submit options to stakeholders at consultation workshop for a choice | Selected intervention option submitted to MOFEP | GWP/CWP |  |  | 0 | 0 | 0 | 0 | 0 | 5 | 5 |
|  |  | Submit selected option to NDPC and MOFEP for funding. |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.1.5 | Deliver project in field | Crop, fish and livestock farmers assisted to implement project in field | The socio economic and environmental conditions of farmers improved. | GWP/CWP, field partners |  |  | 0 | 0 | 0 | 0 | 65 | 25 | 90 |
| OUTPUT 3: Knowledge and capacity developed for enhancing water security and climate resilience | Output indicator 3.1: Number of national, regional and civic organisations with enhanced technical and analytical capacity for assessing the impacts and risks in enabling water security in the context of climate change Output indicator 3.2: Number of decision-makers with enhanced capacity to integrate water security considerations in policy, planning or project implementation. Output indicator 3.3: Number of media features in developing countries on climate resilience & water security Output indicator 3.4: Number of tools for water security & climate resilience developed (incl. analytical inputs to policy/plan/project making; economic analysis of water based ecosystem services; public expenditure reviews) |
| Work Package 6: Capacity Development | Support capacity development of institutions and stakeholders to integrate water security and climate resilience in development plans | Indicators: -Number of institutions able to integrate water security and climate resilience in programs -Number of stakeholders with enhanced capacity to integrate water security and climate change in the design and implementation of policies, plans & projects |  |  | 0 | 0 | 15 | 15 | 10 | 10 | 50 |
|  |  | Key output: Institutions and stakeholders capacitated to integrate water security and climate resilience in development plans |  |  |  |  |  |  |  |  |  |
| Activity 3.1.1 | Develop capacity needs | Map capacity development needs for building water security and climate resilience and | Training needs assessed Capacity development plan prepared | PSC and National Training Coordinator, MMDAs, Consultant |  |  | 0 | 0 | 5 | 5 | 0 | 0 | 10 |
|  |  | Develop capacity development plans in the planning units of the MOFEP, MWRWH, MOFA, MOE, MOTC, MEST, MLNR, MLGRD, WRC, CWSA, GWCL, VRA, FC, EPA, MMDAs etc. These will cover the departments in the sector ministries (PPMEs}, units at the regional level (RPCUs), and the units at the district level (DPCUs). |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.1.2 | Material development | Develop specific materials for training and developing capacities of target audiences. | Training materials made available | GWP, Consultant, MMDAs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Activity 3.1.3 | Developing skills | Identification of water and related sector project in national development plan | Skills of staff in listed institutions improved | GWP, Consultant, MMDAs |  |  | 0 | 0 | 10 | 10 | 10 | 10 | 40 |
|  |  | Screening the water and related sector plans to identify which of them are water secure and climate resilient. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Prioritisation of water secure and climate resilience project to select those that can put forward for investment, because of their no or low regrets investment. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Economic analysis of projects to show that the long term benefits from the intended project will outweigh or equal to the cost of investment |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Development of investment financing strategies |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Project preparation to meet the special requirements of financing agencies. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Monitoring and Evaluation |  |  |  |  |  |  |  |  |  |  |  |
| OUTPUT 4 : Operational GWP network working with strategic allies and stakeholders to integrate water security and climate resilience in the development process | Output indicator 4.1: Number of GWP Network partner organisations with enhanced capacity to manage and develop water resources and increase resilience to climatic variability Output indicator 4.2: Number of RWPs taking corrective measures as a results of GWP annual regional performance review |
| Work Package 7: Knowledge and awareness | Package and disseminate information and knowledge on how to enhance water security and climate resilient development | Indicators: -Number of media features on climate change and water security, all media including radio, television, print, and internet. -Number of publications, knowledge products (including strategic messages) and tools for water security & climate resilience developed and disseminated -Number of joint global/regional activities by GWP and partners on climate change and water security which lead to demonstrable follow-up actions. -User satisfaction across knowledge products and services produced, managed and disseminated by GWP. -Number of south-south lesson learning & knowledge transfers initiatives with commitments for concrete follow up. |  |  | 0 | 10 | 5 | 5 | 7 | 10 | 37 |
|  |  | Key output: Enhanced understanding of the importance of investing in water security and climate resilience at all levels |  |  |  |  |  |  |  |  |  |
| Activity 3.2.1 | Develop Communication strategy: | Develop and implement a communication strategy to create awareness and build political commitment among cabinet ministers, regional and district chief executives, members of parliament particularly the Select Committee on Water, Works and Housing and political party leaders etc. | Communication strategy developed and implemented | GWP/Reg./ Nat |  |  | 0 | 2 | 0 | 0 | 0 | 0 | 2 |
| Activity 3.2.2 | Developing strategic messages | Publish and disseminate policy briefs, fact sheets, briefing notes, Parliamentary briefs key issues on water security, climate resilience , adaptation funds | Various briefs, notes fact sheets published and disseminated Knowledge products made available as appropriate | Consultant, PSC, Communication Officer of CWP and Partners |  |  | 0 | 3 | 0 | 0 | 0 | 0 | 3 |
|  |  | Knowledge products highlighting the role of water development and links to climate change negotiators in the EPA, FC and the Ministry of Foreign Affairs engaged to raise the profile of water in global CC discussions. |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.2.3 | Outreach | Provide media training for the network of journalists in Water on water security and CR issues | Journalist’s knowledge on WS & CR enhanced Support enlisted from journalists to reach out | Consultant, PSC, Communication Officer of CWP and Partners |  |  | 0 | 0 | 2 | 2 | 2 | 5 | 11 |
|  |  | Engage media professionals - especially the association of journalist on water affairs- to support the dissemination of climate information to water managers, industry, farmers, environmentalists and other stakeholders (including the youth and vulnerable groups) to build understanding and inform decisions on water use, allocation and cropping patterns. |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.2.4 | Knowledge sharing: | Support Ghana to gain better access to hydro-meteorological data and better information on state of water resources and climate change impact; | Ghana supported to gain better access to knowledge and up to date information | PSC, CWP and Partners |  |  | 0 | 5 | 3 | 3 | 5 | 5 | 21 |
|  |  | Obtain cutting edge technical and policy approaches to guide decision making for enhancing water security and climate resilience. |  |  |  |  |  |  |  |  |  |  |  |
| Work Package 8: Partnerships and Sustainability | Build capacity of GWP and enhance Regional/ Country level fund raising | Indicators: -Increased programme and financial performance across Regional and Country Water Partnerships -Implementation of Results Framework & associated M&E across the GWP network. |  |  | 11.56 | 16.60 | 15.34 | 15.34 | 60.58 | 60.58 | 180 |
|  |  | Key output: WACDEP efficiently managed and implemented |  |  |  |  |  |  |  |  |  |
| Activity 4.1.1 | Project Management (Secretariat) | Strengthen the CWP Secretariat in 2013 with additional staff of Project Manager, Communication Officer and National Training Coordinator. | Project Manager, Communication Officer and National Training Coordinator recruited Baseline Survey, Work Plan for 2013 to 2015 of the Inception Phase in Q1 of 2013 updated WACDEP launched and validated Information materials prepared and website set up | CWP, GWP, RWP |  |  |  |  |  |  |  |  |  |
|  |  | Update the Baseline Survey, Work Plan for 2013 to 2015 of the Inception Phase in Q1 of 2013 |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Validate and Launch WACDEP. |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Prepare information materials and set up website |  |  |  |  |  |  |  |  |  |  |  |
|  |  Staff Costs |  |  |  |  |  | 8.196 | 8.196 | 11.196 | 11.196 | 44.784 | 44.784 | 128.352 |
|  |  Running Costs |  |  |  |  |  | 0.924 | 0.924 | 0.924 | 0.924 | 3.696 | 3.696 | 11.088 |
|  |  Other Costs |  |  |  |  |  | 1.72 | 1.72 | 1.72 | 1.72 | 6.88 | 6.88 | 20.64 |
|  | fficequipment and furniture Costs |  |  |  |  |  | 0 | 4.26 | 0 | 0 | 0 | 0 | 4.26 |
|  | Regional Travel cost |  |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Activity 4.1.2 | Stakeholder Engagement | Organise the: Ghana post 2015 Consultation Meeting on Water, | Events organised | CWP, TEAMs |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  |  | The General Assembly of the West African Regional Partnership meeting, |  |  |  |  |  |  |  |  |  |  |  |
|  |  | The African Regional Partnership meeting on WACDEP, |  |  |  |  |  |  |  |  |  |  |  |
|  |  | CWP-Ghana Annual General Meeting Steering Committee for WACDEP |  |  |  |  |  |  |  |  |  |  |  |
| Activity 4.1.3 | Strengthening the Network | Strengthen the Steering Committee of CWP to review and guide the WACDEP project implementation by adding representatives from the WRC, NDCP, MOFEP, MWRWH, EPA, MLGRD, MOWAC, Ministry of Lands and Natural Resources. | SC strengthened | CWP, TEAMS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Activity 4.1.4 | Fundraising | Update and resubmit the Proposal for Strengthening the Capacity of District Assemblies for IWRM at the local level. | Proposal resubmitted | CWP, TEAMS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Activity 4.1.5 | Monitoring and evaluation | Monitor WACDEP implementation according to the Monitoring & Evaluation Framework for the programme developed by GWP. | Monitoring and evaluation carried out | CWP, TEAMS |  |  | 0.72 | 1.5 | 1.5 | 1.5 | 5.2 | 5.2 | 15.66 |

Annex 3:  WACDEP GHANA - Implementation Plan (2013 – 2015)

| Item No | WORK PLAN/ACTIVITY DESCRIPTION | RESPON | 2 0 1 3 | 2 0 1 4 | 2 0 1 5 |
| --- | --- | --- | --- | --- | --- |
|  |  | SIBILITY | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
|  | WORK PACKAGE 2: NATIONAL DEVELOPMENT SECTOR PLANS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.1 | • National Assessment | Nat. Consultant |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.2 | • Stakeholder Engagement (Forum) | Nat. Consultant |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.3 | • National Adaptation Responses | Nat. Consultant |  |  |  |  |  |  |  |  |  |  |  |  |
|  | WORK PACKAGE 3: NO/LOW DEGRETS INVESTMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.1 | Prioritise selected projects | Nat. Consultant |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.2 | • Investment Options Appraisal and Analysis | " |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.3 | Assess capacity and organise forum | " |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3.4 | • Integration into National Development Plans | Consultant |  |  |  |  |  |  |  |  |  |  |  |  |
|  | WORK PACKAGE 4: PROJECT PREPARATION AND FINANCE |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.1 | • Enable project preparation | Consultant, GWP,ICA |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.2 | • Appraising and classifying existing investment projects | " |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.3 | • Knowledge Broker and Bridging and Plan Workshop | " |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4.4 | • Resource mobilisation | " |  |  |  |  |  |  |  |  |  |  |  |  |
|  | WORK PACKAGE 5: DEMONSTRATION PROJECTS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.1 | Consultation with stakeholders | GWP/CWP |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.2 | Baseline survey | Consultant |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.3 | Intervention project selection |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.4 | Submit project to NDPC & MOFEP |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.5 | Deliver project in the field |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | WORK PACKAGE 6: CAPACITY DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | • Capacity development needs | Consultant |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 | • Material development | GWP Training |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.3 | • Development skills | " |  |  |  |  |  |  |  |  |  |  |  |  |
|  | WORK PACKAGE 7: KNOWLEDGE AND AWARENESS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | • Communication Strategy | GWP/Reg./Nat. |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.2 | • Developing Strategic Messages | Consultant |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.3 | • Outreach | " |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.4 | • Knowledge Sharing | " |  |  |  |  |  |  |  |  |  |  |  |  |
|  | WORK PACKAGE 8: PARTNERSHIP AND SUSTAINABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.1 | • Project Management | GWP, RWP |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.2 | • Stakeholder Engagement | CWP, TEAMs |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.3 | • Strengthening the Network | " |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.4 | • Fund Raising | " |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1.5 | • Monitoring and Evaluation | " |  |  |  |  |  |  |  |  |  |  |  |  |

# Text boxes

GWP-Ghana Country Partnership

c/o CSIR Water Research Institute

P O Box MB 32

Accra –Ghana

Email  gwpghana@yahoo.com

Telephone +233 302 775135/761031

OUTCOME

4 COMPONETS

8 WORK PACKAGES

Integration, investments in Climate resilient growth and development